## DO NOT EDIT (hidden)
1 | Completed on time
2 | Completed with delay
3 | Delayed
4 | Failed (30 days delay)
5 | Revision required

## Risk Management
|  | RISK MANAGEMENT SHEET | [5 empty] | Doc. QCL-FRM-8.01
Issued: 10-10-2024
Rev: 01
| Last Upated on: | 2024-10-10
RISK ASSESSMENT |  |  |  |  | RISK TREATMENT PLAN
SN | RISK | O | S | RISK RATING | RISK TREATMENT | RESPONSIBILITY | TARGET DATE | Actual Date of Completion | Residual Risk | STATUS | Risk Revision SN
1 | Computer system used for reporting of results, are not provided with password protection which can lead to leakage confidential information | 2 | 5 | 10 | Computer systems are provided with username and password protection. | QCM | 2024-03-03 | 2024-03-03 | Nil | Completed on time
2 | Records kept in printed (hard copy) format are not kept in locked cabinets which can lead to unauthorized access to customer reports. | 2 | 5 | 10 | Records related to customer (such as customer contact information and test reports) are kept in a locked cabinet. | QCM | 2024-04-03 | 2024-04-03 | Nil | Completed on time
3 | Computer system used for storage and documentation of Lab Management System, are not provided with password protection which can lead to leakage information | 2 | 3 | 6 | Computer systems are provided with username and password protection. | QCM | 2024-04-04 | 2024-04-04 | Nil | Completed on time
4 | Some equipment were not calibrated before PT participation which could have increased the risk of PT failure | 2 | 4 | 8 | Calibration plan to be maintained to ensure timely calibration of equipment (through use of Equipment History Log Book) | QCM | 2024-04-05 | 2024-04-05 | Nil | Completed on time
5 | IMPARTIALITY RISKS |  |  | 0
6 | There is a chance that test performers might give favor to customer by modifying test results, which could negatively effect impartiality of the Lab. | 1 | 5 | 5 | VAN QC Lab has ensured that customer cannot directly communicate or interact with test performer without written approval of Management and in their presence only. | QCM | 2024-04-05 | 2024-04-05 | Nil | Completed on time
7 | Performer may not perform the test correctly due to workload and timeline pressures, for the sake of giving results quickly, which can lead to risk of impartiality. | 1 | 5 | 5 | Test results are reviewed by supervisors and management personnel, before it is approved for Reporting to Customer. | QCM | 2024-04-06 | 2024-04-06 | Nil | Completed on time
8 | Performer due to some personal reason does not complete the test process and submits report without complete data requested by customer, which can lead to risk of impartiality. | 1 | 5 | 5 | Test results are reviewed by supervisors and management personnel, before it is approved for Reporting to Customer. | QCM | 2024-04-08 | 2024-04-08 | Nil | Completed on time
9 | One of the superior officers pressurizes the test performer in modifying the test report before dispatch, which can lead to risk of impartiality. | 1 | 5 | 5 | Test results are reviewed by multiple supervisors before the report is approved for dispatch. | QCM | 2024-04-09 | 2024-04-09 | Nil | Completed on time
10 | Customer is able to directly offer money to or put pressure on, test performer, to change the results according to his own will, which can lead to risk of impartiality. | 1 | 5 | 5 | VAN QC Lab has ensured that customer cannot directly communicate or interact with test performer without written approval of Management and in their presence only. | QCM | 2024-04-10 | 2024-04-10 | Nil | Completed on time
11 | Customer is able to directly offer money to or put pressure on, customer service representatives, to modify the reports according to his own will, which can lead to risk of impartiality. | 1 | 5 | 5 | VAN QC Lab has ensured that reports kept under the custody of Customer Representatives (for dispatch) are review and approved by relevant authorities. | QCM | 2024-04-11 | 2024-04-11 | Nil | Completed on time
12 | Ownership: Conflicts of interest may arise if the laboratory is owned by entities with vested interests in the outcomes of tests or research. | 1 | 5 | 5 | QC Lab has Established clear ownership disclosure policies. QC Lab Implements regular audits to identify and mitigate conflicts of interest. | QCM | 2024-09-16 | 2024-04-16 | Nil | Completed on time
13 | Governance: Governance structures may favor certain stakeholders, leading to biased decision-making or prioritization of specific interests. | 1 | 5 | 5 | QC lab has Formed an independent oversight committee to review governance practices and decisions. Regularly assess governance practices against ISO/IEC 17025 2017 standards. | QCM | 2024-09-16 | 2024-09-16 | Nil | Completed on time
14 | Management: Management decisions might be influenced by personal biases or external pressures, compromising impartiality. | 1 | 5 | 5 | QC Lab QCL-LSP-11 for decision-making processes to minimize personal biases. Provide training on impartiality and ethical decision-making. Conduct regular reviews of management decisions and their impacts. | QCM | 2024-04-15 | 2024-09-17 | Nil | Completed on time
15 | Shared Resources: When multiple projects or entities share resources (like equipment or personnel), it may lead to favoritism or inequitable access. | 1 | 5 | 5 | QC Lab has Established clear protocols for resource allocation and usage. Monitor usage patterns to ensure fair access. | QCM | 2024-09-16 | 2024-09-16 | Nil | Completed on time
16 | Performer may not perform test correctly due to lack of understanding of test method or due to absence of sufficient experience, which can compromise impartiality of the lab due to incorrect results. | 3 | 5 | 15 | Supervised Experience VAN QC Lab ensures that pair inexperienced performers with experienced mentors for on-the-job training. Competency Assessments VAN QC Lab ensures conduct initial and periodic competency evaluations through practical tests and written exams. | QCM | 2024-04-16 | 2024-04-16 | Nil | Completed on time
17 | CONFIDENTIALITY RISKS
18 | Customer's information is leaked to unauthorized persons by lab personnel unintentionally, which can lead to breach of confidentiality. | 1 | 5 | 5 | VAN QC Lab ensures that employees are provided with awareness on importance of confidentiality, and the disciplinary measures which may be taken in case of breach. | QCM | 2024-04-18 | 2024-04-18 | Nil | Completed on time
19 | Customer's information is leaked from a computer system available at VAN QC Lab, which can lead to breach of confidentiality. | 1 | 5 | 5 | Computer systems will be provided with username and password protection. | QCM | 2024-04-19 | 2024-04-19 | Nil | Completed on time
20 | Internal documentation is leaked from a computer system available at VAN QC Lab, which can lead to breach of confidentiality. | 1 | 4 | 4 | Computer systems will be provided with username and password protection. | QCM | 2024-04-20 | 2024-04-20 | Nil | Completed on time
21 | Customer is able to access the lab and data available physically, which can lead to breach of confidentiality. | 1 | 5 | 5 | Access to lab sections and computer system are strictly controlled, and customers will not be allowed inside official working areas without authorized escort. | QCM | 2024-04-21 | 2024-04-21 | Nil | Completed on time
22 | Hard Copy files are easily accessible to unauthorized person, which can lead to breach of confidentiality. | 2 | 5 | 10 | All documents and records in hard copy format are stored in locked cabinets, which access to authorized personnel only. | QCM | 2024-04-22 | 2024-04-22 | Nil | Completed on time
23 | PERSONNEL
24 | Untrained person will not be capable of performing the tests correctly and achieving correct results. | 1 | 4 | 4 | Personnel are trained for the tests before they are authorized to perform them, to ensure correct performance and correct results. Competency Assessments VAN QC Lab ensures conduct initial and periodic competency evaluations through practical tests and written exams. | QCM | 2024-04-24 | 2024-04-24 | Nil | Completed on time
25 | Unintentional violations of VAN QC Lab procedures due to lack of understanding of Lab Management System. | 2 | 3 | 6 | Personnel at VAN QC Lab are provided regular trainings on Lab Management System procedures. | QCM | 2024-04-25 | 2024-04-25 | Nil | Completed on time
26 | Test Performer is involved in performing tests which he is not authorized for. | 2 | 5 | 10 | VAN QC Lab has developed Authorization Forms, which ensure that all personnel are communicated about their authorized tests. | QCM | 2024-04-26 | 2024-04-26 | Nil | Completed on time
27 | EQUIPMENT
28 | Equipment may malfunction. | 2 | 3 | 6 | VAN QC Lab ensures that equipment have a regular preventive maintenance plan to prevent malfunctioning. | QCM | 2024-04-28 | 2024-04-28 | Nil | Completed on time
29 | Shared equipment | 2 | 3 | 6 | Same type of tests are allocated to one chemist if its not possible time period will be specified for each analyst. | QCM | 2024-04-29 | 2024-04-29 | Nil | Completed on time
30 | Equipment might not give reliable results. | 2 | 3 | 6 | VAN QC Lab ensured equipment are periodically calibrated through external sources. | QCM | 2024-04-30 | 2024-04-30 | Nil | Completed on time
31 | PURCHASE
32 | Purchase of unreliable equipment and supplies. | 1 | 4 | 4 | VAN QC Lab ensured evaluation suppliers before approving them for purchase of items. | QCM | 2024-05-02 | 2024-05-02 | Nil | Completed on time
33 | Purchased equipment does not have all the requirements and features. | 1 | 4 | 4 | VAN QC Lab ensured that purchase requests are properly documents and purchased items are inspected before they are accepted. | QCM | 2024-05-03 | 2024-05-03 | Nil | Completed on time
34 | ITEMS MANAGEMENT
35 | Chemicals and reagents have expired due to lack of proper storage facility. | 1 | 4 | 4 | Chemicals and reagents are stored in a temperature controlled environment. | QCM | 2024-05-05 | 2024-05-05 | Nil | Completed on time
36 | Wastage and misuse of Chemicals and reagents. | 1 | 4 | 4 | VAN QC Lab will implement inventory management system to ensure control over usage of chemicals and reagents. | QCM | 2024-05-06 | 2024-05-06 | Nil | Completed on time
37 | ENVIRONMENT
38 | Test environment temperature is out of limits. | 5 | 3 | 15 | VAN QC Lab has installed air conditioners and monitors temperature regularly, to ensure that temperature remains within limits. | QCM | 2024-05-08 | 2024-05-08 | Nil | Completed on time
39 | Test environment humidity is out of limits. | 5 | 3 | 15 | VAN QC Lab has installed air conditioners and monitors humidity regularly, to ensure that humidity remains within limits. | QCM | 2024-05-09 | 2024-05-09 | Nil | Completed on time
40 |  |  |  | 0
41 |  |  |  | 0
42 |  |  |  | 0
43 |  |  |  | 0
44 |  |  |  | 0
45 |  |  |  | 0

## Criteria
Doc. QCL-FRM-8.01
Issued: 10-OCT-2024
Rev: 01
RATING | DESCRIPTION
Chances of Occurrence (O)
1 | The existing measures or nature of work ensure that risk has almost no chances of occurrence
2 | The risk has occurred once in the last 12 months based on existing measures
3 | The risk has occurred once in the last 6 months based on existing measures
4 | The risk has occurred once in the last 30 days based on existing measures
5 | The risk has occurred more than once in the last 30 days
Severity of Impact (S)
1 | The existing measures or nature of work ensure that risk occurrence has almost no noticeable impact on organization business objectives, processes and services
2 | Based on existing measures, risk only impacts a minor process which does not directly effect any customer based requirements, or primary services offered by the organization
3 | Based on existing measures, risk impacts a process of the organization which is one of the support functions for one of the primary services, but without effecting customer’s asset, information and/or requirements
4 | Based on existing measures, risk impacts one of the primary processes of the organization, which can negatively effect customer related services as well as major requirements of Management System (Standard) Implemented including effecting measures taken to prevent impartiality, but without effecting customer’s asset or information
5 | Based on existing measures, risk impacts more than one primary processes of the organization, which can negatively effect customer related services and also might compromise impartiality and confidentiality measures, including the ones associated with customers, their assets and information

## Heat Chart
|  | Heat Chart |  | Doc. QCL-FRM-8.01
Issued: 01-Oct-2024
Rev: 01
RISK HEAT CHART |  | S
|  | 1 | 2 | 3 | 4 | 5
O | 1 | 1 | 2 | 3 | 4 | 5
| 2 | 2 | 4 | 6 | 8 | 10
| 3 | 3 | 6 | 9 | 12 | 15
| 4 | 4 | 8 | 12 | 16 | 20
| 5 | 5 | 10 | 15 | 20 | 25
Risk Rating is ignorable
Risk Rating is Noteworthy and should be taken care of
Risk Rating is Critical and must be taken care of immediately